## Sheet1
St Date | End Date | Task ID | Task Description | 3WLA Task Description | Resources | Quantity | Responsible Manager | Location | Chainage From | Chainage To
2019-04-19 | 2019-04-19 | A0001 | A J Wilcox Rock Saw Cut- Section 2B1 52850 - 54750 (1900m) | 1st Rock Saw Cut | A J Willcock Gang 1 | 100 | Chris Nolan | A Track | 54000 | 54800
2019-04-19 | 2019-04-19 | A0001 | A J Wilcox Rock Saw Cut- Section 2B1 52850 - 54750 (1900m) | 1st Rock Saw Cut | A J Willcock Gang 1 |  | Chris Nolan | A Track | 54800 | 55000
2019-03-29 | 2019-03-29 | A0001 | A J Wilcox Rock Saw Cut- Section 2B1 52850 - 54750 (1900m) | 1st Rock Saw Cut | A J Willcock Gang 2 |  | Chris Nolan | A Track | 52800 | 53000
2019-04-01 | 2019-04-01 | A0001 | A J Wilcox Rock Saw Cut- Section 2B1 52850 - 54750 (1900m) | 1st Rock Saw Cut | A J Willcock Gang 2 |  | Chris Nolan | A Track | 53600 | 54000
2019-03-30 | 2019-03-30 | A0001 | A J Wilcox Rock Saw Cut- Section 2B1 52850 - 54750 (1900m) | 1st Rock Saw Cut | A J Willcock Gang 2 |  | Chris Nolan | A Track | 54000 | 54400
2019-03-30 | 2019-03-30 | A0001 | A J Wilcox Rock Saw Cut- Section 2B1 52850 - 54750 (1900m) | 1st Rock Saw Cut | A J Willcock Gang 2 |  | Chris Nolan | A Track | 54400 | 54800
2019-04-19 | 2019-04-19 | A0001 | A J Wilcox Rock Saw Cut- Section 2B1 52850 - 54750 (1900m) | 1st Rock Saw Cut | A J Willcock Gang 2 |  | Chris Nolan | A Track | 54800 | 55000
2019-04-08 | 2019-04-08 | A0001 | A J Wilcox Rock Saw Cut- Section 2B1 52850 - 54750 (1900m) | 2nd Rock Saw Cut | A J Willcock Gang 1 |  | Chris Nolan | A Track | 53000 | 53100
2019-04-08 | 2019-04-08 | A0001 | A J Wilcox Rock Saw Cut- Section 2B1 52850 - 54750 (1900m) | 2nd Rock Saw Cut | A J Willcock Gang 1 |  | Simon Powell | B Track | 53100 | 53200
2019-04-08 | 2019-04-08 | A0001 | A J Wilcox Rock Saw Cut- Section 2B1 52850 - 54750 (1900m) | 2nd Rock Saw Cut | A J Willcock Gang 1 |  | Simon Powell | B Track | 53200 | 53400
2019-04-09 | 2019-04-09 | A0001 | A J Wilcox Rock Saw Cut- Section 2B1 52850 - 54750 (1900m) | 2nd Rock Saw Cut | A J Willcock Gang 1 |  | Simon Powell | B Track | 53200 | 53300
2019-04-09 | 2019-04-09 | A0001 | A J Wilcox Rock Saw Cut- Section 2B1 52850 - 54750 (1900m) | 2nd Rock Saw Cut | A J Willcock Gang 1 |  | Simon Powell | B Track | 53800 | 54000
2019-04-09 | 2019-04-09 | A0001 | A J Wilcox Rock Saw Cut- Section 2B1 52850 - 54750 (1900m) | 2nd Rock Saw Cut | A J Willcock Gang 1 |  | Simon Powell | B Track | 54100 | 54200
2019-04-09 | 2019-04-09 | A0001 | A J Wilcox Rock Saw Cut- Section 2B1 52850 - 54750 (1900m) | 2nd Rock Saw Cut | A J Willcock Gang 1 |  | Simon Powell | B Track | 54200 | 54300
2019-04-12 | 2019-04-12 | A0002 | Vaccum excavation of exclusion zones - Section 2B1 52850 - 54750 (1900m) | Vac Ex - Trial holes Extensions | BBV Gang 1 |  | Richard H | Central Reservation | 52800 | 53000
2019-04-13 | 2019-04-13 | A0002 | Vaccum excavation of exclusion zones - Section 2B1 52850 - 54750 (1900m) | Vac Ex - Trial holes Extensions | BBV Gang 1 |  | Richard H | Central Reservation | 52800 | 53000
2019-04-15 | 2019-04-15 | A0002 | Vaccum excavation of exclusion zones - Section 2B1 52850 - 54750 (1900m) | Vac Ex - Trial holes Extensions | BBV Gang 1 |  | Richard H | Central Reservation | 52800 | 53000
2019-04-16 | 2019-04-16 | A0002 | Vaccum excavation of exclusion zones - Section 2B1 52850 - 54750 (1900m) | Vac Ex - Trial holes Extensions | BBV Gang 1 |  | Richard H | Central Reservation | 52800 | 53000
2019-04-17 | 2019-04-17 | A0002 | Vaccum excavation of exclusion zones - Section 2B1 52850 - 54750 (1900m) | Vac Ex - Trial holes Extensions | BBV Gang 1 |  | Richard H | Central Reservation | 52800 | 53000
2019-04-15 | 2019-04-15 | A003 | Hand dig of exclusion zones - Section 2B1 52850 - 54750 (1900m) (Approx 8 No) | Hand dig of exclusion zones | Gangs NSWRA | 8 No | Richard H | Central Reservation | 54000 | 55000
2019-04-16 | 2019-04-16 | A003 | Hand dig of exclusion zones - Section 2B1 52850 - 54750 (1900m) (Approx 8 No) | Hand dig of exclusion zones | Gangs NSWRA | 6 No | Richard H | Central Reservation | 54000 | 55000
2019-04-17 | 2019-04-17 | A003 | Hand dig of exclusion zones - Section 2B1 52850 - 54750 (1900m) (Approx 8 No) | Hand dig of exclusion zones | Gangs NSWRA | 4 No | Richard H | Central Reservation | 54000 | 55000
2019-04-18 | 2019-04-18 | A003 | Hand dig of exclusion zones - Section 2B1 52850 - 54750 (1900m) (Approx 8 No) | Hand dig of exclusion zones | Gangs NSWRA | 2 No | Richard H | Central Reservation | 54000 | 55000